## Slide 1: A Project Financier's Standpoint |Risk Assessment in IPF|
10th Feb, 2014
|Project & Structured Finance|Investment Banking Group|
|P r e s e n t a t i o n|
|UNITED BANK LIMITED|

## Slide 2: Note
Please note that the following slides contain information on certain project finance transactions that have taken place in the Pakistan financial markets over the last 8 years.
The information presented herein is aimed at sharing key risks that manifested themselves during construction period or over the initial operating life of the project(s) and how the Project Financiers dealt with them (or should have dealt with them) given the Project Finance framework as enshrined in the IPF Guidelines issued by the SBP and/or internal policies governing PF transactions, issued by banks and FIs for internal stakeholders’ consumption.
The details and specifics of transactions mentioned are from an academic and learning standpoint only and should not be construed as being reflective of the respective projects or any of their stakeholders in any manner.
|Project & Structured Finance|UNITED BANK LIMITED|

## Slide 3: Contents
Definition
Risk Matrix
The Adequacy of LDs
Short Case Studies

## Slide 4: Definition
A method of funding whereby a company obtains financing for specific assets by giving creditors claim on the revenues generated by those assets. The created entity’s only asset is the ‘Project’.
A way of financing whereby risks that cannot be mitigated through structuring are passed on to stakeholders that are ‘best-capable’ of managing those risks.
Principle of ‘Equitable Allocation.’

## Slide 5: Characteristics
Usually raised for a new project rather than an established business.
Generally high debt:equity ratio.
No guarantees from the investors (‘non-recourse’), or limited guarantees (‘limited-recourse’) for the project finance debt.
Reliance on future cash flows of the Project for debt servicing rather than value of its assets and/or operational history.
Main security for lenders is the Project’s contracts, licenses or ownership of rights to natural resources; physical assets likely to be worth much less than the debt if they are sold off after a default on financing.
Finite life, based on such factors as the length of the contracts, concessions, licenses or the reserves of natural resources.

## Slide 6: A bit of history…
Roman and Greek merchants used this technique to share risks inherent in maritime trading.
  Loan would be advanced to a shipping merchant on the agreement that such loan would be repaid only through the sale of cargo brought back by the voyage (i.e. internally generated cashflows).
In modern history, used for developing Panama Canal (1914).
Adopted widely during the ‘70s for development of North Sea oilfields.
Most prolific use is UK’s Private Finance Initiative (PPP regime) in ’92 for infrastructure spanning schools, hospitals, prisons and roads.

## Slide 7: Global Perspective
Global PF market size circa USD 200bn (2012)
Top sectors include: Power, Oil & Gas and Transport (approx. 70-80%).
Europe and Asia Pacific two biggest markets for IPF.
Bank loans still provide over 70% of debt capital for IPF (bonds: 10-15%).
Debt markets struggling with sovereign ratings and Basel III.
Increasing reliance on MLAs and ECAs.

## Slide 8: Typical PF Stakeholders
PROJECT COMPANY
Equity Investor
Equity Investor
Equity Contribution Agreement
Shareholder’s
Agreement
Commercial Lenders
Sponsor’s Legal Counsel
Lender’s Legal Counsel
Contractor
Equipment Supplier
Design Consultant
Raw Materials & Utilities
Market/ Off-taker
Agent/Trustee/Monitoring
Ceding Authority
Lenders’ Technical & Insurance Consultants
Operator/ O&M*
Loan Agreement/ Security Package
Agency Agreement
End Product
Supply Contracts
Concession Agreement
Supply / EPC Contract
O&M Contract
Assignments/Guarantees/ Direct Agreements
Owner’s Technical & Insurance Consultants
Legend:
: means contractual relationship
means informal relationship

## Slide 9: PF Methodology
Risk Evaluation
Bankable Term Sheet
Identification of Sources of Finance
Project Structuring
Negotiation of Financing & Security Documents
Financial DD - Modeling and Analysis
Legal DD – Review of Project Contracts to identify gaps with lenders’ legal counsel
Technical DD - Review of model and Project Documents for technical sufficiency and reasonableness
Financial Close

## Slide 10: Contents
Definition
Risk Matrix
The Adequacy of LDs
Short Case Studies

## Slide 11: Risk Matrix: Construction
Risk |  | 
Cost Overrun-contractor’s control |  | 
Cost Overrun-Insured |  | 
Uninsured FM Event |  | 
Cost Overrun-Change in Law |  | 
Completion delay-contractor’s control |  | 
Completion Delay-Insured |  | 
Completion-Performance shortfall |  | 
i, fx, inflation |  | 

## Slide 12: Risk Matrix: Operations
Risk |  | 
Operating Cost overrun-Govt fault |  | 
Operating Cost overrun-Operator fault |  | 
i, fx, inflation |  | 
Fx restrictions/controls |  | 
Country risk (nationalization etc) |  | 
Operator default |  | 
Power purchaser default |  | 
Equipment failure |  | 

## Slide 13: Contents
Definition
Risk Matrix
The Adequacy of LDs
Short Case Studies

## Slide 14: Liquidated Damages (‘LDs’)
LDs are damage penalties payable in advance as a pre-estimate of loss for failure to perform.
Usually payable for:
  Delay (DLDs)
  Performance (PLDs/Buy-down LDs)

## Slide 15: Adequacy of LDs
Under EPC contract, review DLDs in context of:
  DLDs payable by SPV under PPA
  LDs under other Project Agreements as GSA etc
  Roll-up of IDC and other costs during delay
  Fixed O&M costs
Total Cap = DLD cap + PLD cap
Total Cap: Usually 10-15% of contract price
LDs assigned to lenders-key project security

## Slide 16: The LD Adequacy Matrix
Typically, for an IPP, Lenders demand a 6-month coverage of LDs payable and Fixed Costs incurred by the Project.
Delay Period | US$ (m)

## Slide 17: Contents
Definition
Risk Matrix
The Adequacy of LDs
Short Case Studies

## Slide 18: Thank you
|M. Umer Khan|SVP & Head, Project & Structured Finance|
|Investment Banking Group|UNITED BANK LIMITED|
|Umer.Khan@ubl.com.pk|021 3241.1846|